## Project Planner
Roskilde daycare
Gantt chart |  |  |  |  | Period Highlight: | 1 | Plan Duration |  | Actual Start |  | % Complete |  |  |  | Actual (beyond plan) |  |  |  | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 17 | 18 | 19 | 20 | 21 |  | 22 |  | 23 |  |  | 24 | 25 | 26 | 27
Brainstorm needs + requirements | 17 | 1 | 17 | 1 | 100% |  | Thomas, Ilias, Rasmus, Cris, David
FURPS+ | 18 | 1 | 18 | 1 | 100% |  |  | Thomas, Ilias, Rasmus, Cris, David
Use Cases | 18 | 2 | 18 | 2 | 100% |  |  |  | Thomas, Ilias, Rasmus, Cris, David
Feasibility Study | 19 | 1 | 19 | 2 | 100% |  |  |  |  | David
Conceptual Model | 19 | 1 | 19 | 1 | 100% |  |  |  | Ilias
Class Diagram | 19 | 1 | 19 | 1 | 100% |  |  |  | Rasmus, Cris, Thomas
Design software prototype | 19 | 1 | 19 | 1 | 100% |  |  |  | David
Paper prototype for UX | 20 | 1 | 22 | 1 | 100% | [8 empty] | Ilias
Code foundation of program | 20 | 1 | 20 | 1 | 100% |  |  |  |  | David
Code menus and login | 20 | 2 | 20 | 2 | 100% | [6 empty] | Cris
Code assorted functions | 20 | 2 | 20 | 4 | 100% | [11 empty] | Thomas, Ilias, Rasmus, Cris, David
Code payments/invoice system | 20 | 2 | 20 | 1 | 100% | [6 empty] | Ilias
Code file management | 20 | 2 | 20 | 2 | 100% | [6 empty] | Thomas
First major System test | 23 | 1 | 23 | 1 | 100% | [11 empty] | Thomas, Ilias, Rasmus, Cris, David
SQL database draft | 24 | 1 | 24 | 1 | 100% | [12 empty] | Cris, Rasmus
SQL database creation | 25 | 2 | 25 | 1 | 100% | [7 empty] | Cris
Final System test | 26 | 1 | 26 | 1 | 100% | [10 empty] | Thomas, Ilias, Rasmus, Cris, David
Live test with Focus Group | 26 | 1 | 26 | 1 | 100% | [10 empty] | Thomas, Ilias, Rasmus, Cris, David